## Project plan summary
/Proyecto/PSP Fundamentals & Advanced/Program 4
PSP2 Project Plan Summary
Project Settings
Project Owner | Daniel Melgarejo
Start Date | mar 20, 2017 10:13:00 AM
Completion Date | mar 21, 2017 11:39:17 PM |  |  |  | Completed: *
Keywords | Programa 4
Language | Java
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 44.9 | 9.1 | 35.4
Planned Time | 0.18194 |  | 0.33333
Actual Tiempo |  | 0.12361 | 0.64931
CPI (Cost-Performance Index) |  |  | 0.79
% Reuse | 24.3% | 34.9% | 14.9%
% New Reusable | 0% | 0% | 63.2%
Test Defects/KLOC or equivalent | 3.82 | 0 | 3.63
Total Defects/KLOC or equivalent | 11.5 | 111 | 16.3
Yield % | 66.7% | 100% | 77.8%
Code Review Rate | 1478 | 180 | 1033
Program Size
| Plan | Actual | A la Fecha
Base (B) | 50 | 150 | 209
Deleted (D) | 0 | 0 | 0
Modified (M) | 0 | 20 | 28
Added (A) | 196 | 7 | 523
Reused (R) | 79 | 84 | 128
Added and Modified (A+M) | 196 | 27 | 551
Total Size (T) | 325 | 241 | 860
Total New Reusable | 0 | 0 | 348
Estimated Proxy Size (E) | 238 | 261 | 873
Time In Phase
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.026389 | 0.025 | 0.10139 | 15.6%
DiseÃ±o | 0.015972 | 0.015278 | 0.061806 | 9.52%
RevisiÃ³n de DiseÃ±o | 0.0055556 | 0.0083333 | 0.023611 | 3.64%
CodificaciÃ³n | 0.063889 | 0.044444 | 0.22778 | 35.1%
RevisiÃ³n de CodificaciÃ³n | 0.0055556 | 0.00625 | 0.022222 | 3.42%
CompilaciÃ³n | 0.0013889 | 0 | 0.0034722 | 0.53%
Pruebas | 0.047222 | 0.024306 | 0.16111 | 24.8%
Postmortem | 0.016667 | 0 | 0.047917 | 7.38%
Total | 0.18194 | 0.12361 | 0.64931
Defects Injected
| Plan | Actual | A la Fecha | % A la Fecha
Antes de Desarrollo | 0 | 0 | 0 | 0%
PlaneaciÃ³n | 0 | 1 | 1 | 11.1%
DiseÃ±o | 1.12 | 0 | 3 | 33.3%
RevisiÃ³n de DiseÃ±o | 0 | 0 | 0 | 0%
CodificaciÃ³n | 1.12 | 2 | 5 | 55.6%
RevisiÃ³n de CodificaciÃ³n | 0 | 0 | 0 | 0%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0 | 0 | 0 | 0%
Total | 2.25 | 3 | 9
Defects Removed
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 0 | 1 | 1 | 11.1%
RevisiÃ³n de DiseÃ±o | 0.37 | 0 | 1 | 11.1%
CodificaciÃ³n | 1.12 | 2 | 5 | 55.6%
RevisiÃ³n de CodificaciÃ³n | 0 | 0 | 0 | 0%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0.75 | 0 | 2 | 22.2%
Total | 2.25 | 3 | 9
After Development | 0.75 | 0 | 2
Defect Removal Efficiency
| Plan | Actual | A la Fecha
Defects/Hour - Design Review | 2.95 | 0 | 1.76
Defects/Hour - Code Review | 0 | 0 | 0
Defects/Hour - Compile | 0 | #DIV/0! | 0
Defects/Hour - Test | 0.66 | 0 | 0.52
DRL (DLDR/UT) | 4.48 | 0 | 3.41
DRL (Code Review/UT) | 0 | 0 | 0
DRL (Compile/UT) | 0 | #DIV/0! | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:39 PM el 21/03/2017